## Sheet1
Agile Project Plan
Project Name | Mon Ngon
Project Manager | Lê Minh Trí
Project Deliverable
Scope Statement
Start Date | 2018-04-04
End Date | 2018-05-22
Overall Progress | 20%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Lê Minh Trí | 2018-04-04 | 2018-04-17 | 30 hours | Not started
Login screen | Lê Nguyễn Hoàng Huynh | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Registration screen | Lê Nguyễn Hoàng Huynh | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Home screen | Hoàng Nhật Sơn | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Location Screen | Lê Minh Trí | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Search function | Hoàng Nhật Sơn | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
User Screen | Nguyễn Phúc Toàn | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Area Screen | Nguyễn Phúc Toàn | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
The dialog box comments the product post | Đặng Văn Sơn | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Screen about us | Nguyễn Thành Công | 2018-04-04 | 2018-04-11 | 18.75 hours | Not started
Sprint 2 | Jacob S. | 2018-04-18 | 2018-05-01 | 30 hours | Not started
Dialog screen selects image function | Đặng Văn Sơn | 2018-04-18 | 2018-04-25 | 18.75 hours | Not started
Enterprise details screen | Lê Minh Trí | 2018-04-18 | 2018-04-25 | 18.75 hours | Not started
Product detail screen | Lê Minh Trí | 2018-04-18 | 2018-04-25 | 18.75 hours | Not started
Update business information | Nguyễn Thành Công | 2018-04-18 | 2018-04-25 | 18.75 hours | Not started
Personal details screen | Lê Minh Trí | 2018-04-18 | 2018-04-25 | 18.75 hours | Not started
Sprint 3 | Lê Minh Trí | 2018-05-02 | 2018-05-15 | 30 hours | Not started
Editing products Screen | Nguyễn Minh Trí | 2018-05-02 | 2018-05-09 | 18.75 hours | Not started
Adds products Screen | Nguyễn Minh Trí | 2018-05-02 | 2018-05-09 | 18.75 hours | Not started
Commentary business Screen | Đặng Văn Sơn | 2018-05-02 | 2018-05-09 | 18.75 hours | Not started
Monitor product management | Nguyễn Minh Trí | 2018-05-02 | 2018-05-09 | 18.75 hours | Not started