## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Home Screen | 18,75 | Hoàng Nhật Sơn | Not started
Button Home |  |  |  | 5 | 5 | 0 | 0 | 0 | 0 | 0
Button Place |  |  |  | 5 | 3 | 2 | 0 | 0 | 0 | 0
Button Area |  |  |  | 5 | 5 | 0 | 0 | 0 | 0 | 0
Button User(Person) |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
List of places, restaurants list |  |  |  | 0,75 | 0,75 | 0 | 0 | 0 | 0 | 0
Product Detail Screen | 18,75 | Lê Minh Trí | Not started
Button back |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
Display information |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
Button contact |  |  |  | 8,75 | 0 | 0 | 0 | 0 | 0 | 0
Place Screen | 18,75 | Lê Minh Trí | Not started
Tab selection menu |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Listview |  |  |  | 8,75 | 0 | 0 | 0 | 0 | 0 | 0
Area Screen | 18,75 | Nguyễn Phúc Toàn | Not started
Show individual locations, businesses around |  |  |  | 18,75 | 0 | 0 | 0 | 0 | 0 | 0
User Screen | 18,75 | Nguyễn Phúc Toàn | Not started
Show selected lines: - Personal page - Manage posts - Logout - About us |  |  |  | 18,75 | 0 | 0 | 0 | 0 | 1 | 0
Business Detail Screen | 18,75 | Lê Minh Trí | Not started
Button Contact |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0
Show location information |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0
Display map |  |  |  | 2,75 | 0 | 0 | 0 | 0 | 0 | 0
About us screen #7 | 18,75 | Nguyễn Thành Công | Not started
ImageView App name |  |  |  | 5 | 5 | 0 | 0 | 0 | 0 | 0
TextView Descreption |  |  |  | 5 | 5 | 0 | 0 | 0 | 0 | 0
TextView addres |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
TextView Hotline phone |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
TextView Version |  |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0
Button Back |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Edit product screen | 18,75 | Nguyễn Minh Trí | Not started
Button Add image |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 0
EditText Product Name |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 0
EditText Product Price |  |  |  | 5 | 0 | 5 | 0 | 0 | 0 | 0
EditText Product Descreption |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0
Button Edit Product |  |  |  | 5 | 0 | 5 | 0 | 0 | 0 | 0
Button Back |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Add product screen | 18,75 | Nguyễn Minh Trí | Not started
Button Add image |  |  |  | 5 | 0 | 5 | 0 | 0 | 0 | 0
EditText Product Name |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 0
EditText Product Price |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 0
EditText Product Descreption |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0
Button Add Product |  |  |  | 5 | 0 | 5 | 0 | 0 | 0 | 0
Button Back |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Post list screen | 18,75 | Nguyễn Minh Trí | Not started
Add products button |  |  |  | 5 | 0 | 0 | 5 | 0 | 0 | 0
ListView Posts |  |  |  | 5 | 0 | 0 | 5 | 0 | 0 | 0
Page Title |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
Edit button |  |  |  | 3 | 0 | 0 | 3 | 0 | 0 | 0
Delete button |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0
Function button |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0
Back Button |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Update business information | 18,75 | Nguyễn Thành Công | Not started
Add image business button |  |  |  | 7 | 0 | 0 | 7 | 0 | 0 | 0
EditText Business Name |  |  |  | 3 | 0 | 0 | 3 | 0 | 0 | 0
EditText Business Hotline |  |  |  | 3 | 0 | 0 | 3 | 0 | 0 | 0
EditText Working time |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0
EditText Business addres |  |  |  | 3 | 0 | 0 | 3 | 0 | 0 | 0
Back Button |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Personal detail | 18,75 | Lê Minh Trí | Not started
ImageView business |  |  |  | 7 | 0 | 0 | 0 | 7 | 0 | 0
TextView Business Name |  |  |  | 3 | 0 | 0 | 0 | 3 | 0 | 0
TextView Business Hotline |  |  |  | 3 | 0 | 0 | 0 | 3 | 0 | 0
TextView Working time |  |  |  | 3 | 0 | 0 | 0 | 3 | 0 | 0
TextView Business addres |  |  |  | 2 | 0 | 0 | 0 | 2 | 0 | 0
Back Button |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Comment product | 18,75 | Đặng Văn Sơn | Not started
recycle view for product reviews |  |  |  | 8 | 5 | 3 | 0 | 0 | 0 | 0
sinpper |  |  |  | 5 | 2 | 1 | 2 | 0 | 0 | 0
list view display the list |  |  |  | 3 | 1 | 2 | 0 | 0 | 0 | 0
Valuation Screen has 1 serch view |  |  |  | 2,75 | 1 | 1.75 | 0 | 0 | 0 | 0
Screen dialogue selects the image function | 18,75 | Đặng Văn Sơn | Not started
Add a photo to add image |  |  |  | 8 | 4 | 2 | 2 | 0 | 0 | 0
A framework for entering a product name |  |  |  | 5 | 2 | 1 | 2 | 0 | 0 | 0
A framework for entering a product price |  |  |  | 3 | 1 | 2 | 0 | 0 | 0 | 1
A framework for entering a product description |  |  |  | 2.75 | 1 | 1.75 | 0 | 0 | 0 | 0
Business Comment | 18,75 | Đặng Văn Sơn | Not started
Send button |  |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0
Comment list |  |  |  | 6 | 2 | 4 | 0 | 0 | 0 | 0
Back button |  |  |  | 8..75 | 5 | 3.75 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product manager Screen | 18,75 | Nguyễn Minh Trí | Not started
Close button |  |  |  | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Product function button |  |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0
Add button |  |  |  | 6 | 3 | 3 | 0 | 0 | 0 | 0
Product list |  |  |  | 10 | 5 | 5 | 0 | 0 | 0 | 0
Register Screen | 18,75 | Lê Nguyễn Hoàng Huynh | Not started
Tab Type Register |  |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0
Normal Register |  |  |  | 6 | 2 | 4 | 0 | 0 | 0 | 0
Business Register |  |  |  | 8..75 | 5 | 3.75 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Login Screen | 18,75 | Lê Nguyễn Hoàng Huynh | Not started
Tab Type ( Login - Register ) |  |  |  | 8.75 | 2 | 2 | 2 | 2 | 0.75 | 0
Login |  |  |  | 10 | 2 | 2 | 2 | 2 | 2 | 0
Total |  |  |  | 69.75 | 45 | 30.5 | 8 | 4 | 2 | 1